## Sheet1
Prashanth | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Worked on designing a part of UI Wireframes, Update Sprint Journal
|  | What am I planning to do to next? | Revise the UI Wireframes and start the Front End Development
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Revised and made changes in UI Wireframes and started Front End Development, Update Sprint Journal
|  | What am I planning to do to next? | Start building user interface for Landing, Signup, Login Pages
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Finished building user interface for Landing, Signup, Login Pages, Update Sprint Journal
|  | What am I planning to do to next? | Start building user interface for Dashboard, Booking rooms.
|  | What tasks are blocked waiting on another team member? | Integration with backend functionalities of Signup and Login
| Sprint 4 | What task did I work on/complete? | Integrated Signup and Login with Backend APIs and Completed UI for Dashboard, Search hotel, book hotel
|  | What am I planning to do to next? | Integrating Dashboard, Search hotel, Book hotel with backend APIs and start building UI for update reservation
|  | What tasks are blocked waiting on another team member? | Integration with backend functionalities of Dashboard.
| Sprint 5 | What task did I work on/complete? | Integrated dashboard, search hotel, modify booking with backend API and completed UI for update reservation
|  | What am I planning to do to next? | Integrating update reservation with backend API and start building UI for cancel booking
|  | What tasks are blocked waiting on another team member? | Integration with backend functionalities of modify reservation
| Sprint 6 | What task did I work on/complete? | Integrated update reservation with backend API and completed UI for cancel booking
|  | What am I planning to do to next? | Integrating modify reservation with backend API and deploying application, documentation
|  | What tasks are blocked waiting on another team member? | Integration with backend functionalities of dynamic pricing
| Sprint 7 | What task did I work on/complete? | Integrated modify reservation with Backend APIs
What am I planning to do to next?
What tasks are blocked waiting on another team member?
Abhinav | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Worked on designing a part of the system architecture, getting started with the githhub projects tool(similar to trello to and JIRA)
|  | What am I planning to do to next? | Revise the system architecture and start the Back End Development
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Revised the system architecture and started the Back End Development, plan user stories for the team
|  | What am I planning to do to next? | Start building backend functionalities of Login and singup for user
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Login and Signup APIs for user, Involved in DB design,
|  | What am I planning to do to next? | Create landing page for user
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Create landing page for user, create user stories for sprint 4, peer review
|  | What am I planning to do to next? | Building adding a hotel, adding a room APIs
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Built adding a hotel, adding a room APIs
|  | What am I planning to do to next? | Listing all hotels for admin API, view all bookings API
|  | What tasks are blocked waiting on another team member? | None
| Sprint 6 | What task did I work on/complete? | Listing all hotels for admin API, view all bookings API
|  | What am I planning to do to next? | View hotel bookings for admin API, deployment
|  | What tasks are blocked waiting on another team member? | None
| Sprint 7 | What task did I work on/complete? | View hotel bookings for admin API, deployment
|  | What am I planning to do to next? | End of Sprints
|  | What tasks are blocked waiting on another team member? | None
Rakshith | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Worked on designing a part of the system architecture, Burndown chart
|  | What am I planning to do to next? | Revise the system architecture and start the Back End Development
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Revised the system architecture and started the Back End Development, Burndown chart
|  | What am I planning to do to next? | Backend Setup and Start building backend functionalities of Signup
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Finished Backend Setup and Started building backend functionalities of Signup, Burndown chart
|  | What am I planning to do to next? | Revise System Architecture, book rooms API, get bookings API API, Burndown chart
|  | What tasks are blocked waiting on another team member? | None
| Sprint 4 | What task did I work on/complete? | Revise System Architecture, book rooms API, get bookings API , Burndown chart
|  | What am I planning to do to next? | check room avalability and modify reservation, Burndown chart
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | check room avalability and modify reservation, Burndown chart
|  | What am I planning to do to next? | Cancel bookings API, Integrate UI with book rooms API , Burndown chart
|  | What tasks are blocked waiting on another team member? | None
| Sprint 6 | What task did I work on/complete? | Cancel bookings API, Integrate UI with book rooms API , Burndown chart
|  | What am I planning to do to next? | Deployment of Application on Cloud, Burndown chart, Peer review
|  | What tasks are blocked waiting on another team member? | None
| Sprint 7 | What task did I work on/complete? | Deployment of Application on Cloud, Burndown chart, Peer review
What am I planning to do to next?
|  | What tasks are blocked waiting on another team member? | None
Iswarya | Sprint Details | Tasks
| Sprint 1 | What task did I work on/complete? | Worked on designing a part of UI Wireframes, Update Weekly scrum report
|  | What am I planning to do to next? | Revise the UI Wireframes and start the Front End Development
|  | What tasks are blocked waiting on another team member? | None
| Sprint 2 | What task did I work on/complete? | Revised the UI Wireframes and started the Front End Development, Update Weekly scrum report
|  | What am I planning to do to next? | Start building user interface for User landing page
|  | What tasks are blocked waiting on another team member? | None
| Sprint 3 | What task did I work on/complete? | Completed the UI for the Profile page, Update Weekly scrum report
|  | What am I planning to do to next? | Integrate Admin Page with backend
|  | What tasks are blocked waiting on another team member? | Integration with search hotels API
| Sprint 4 | What task did I work on/complete? | Integrate Admin Page with backend
|  | What am I planning to do to next? | Admin login and dashboard
|  | What tasks are blocked waiting on another team member? | None
| Sprint 5 | What task did I work on/complete? | Admin login and dashboard
|  | What am I planning to do to next? | Intergrate UI with get bookings API
|  | What tasks are blocked waiting on another team member? | None
| Sprint 6 | What task did I work on/complete? | Intergrate UI with get bookings API
|  | What am I planning to do to next? | End to end testing and Deployment on cloud
|  | What tasks are blocked waiting on another team member? | None
| Sprint 7 | What task did I work on/complete? | End to End testing, Peer review, Deployment on cloud, Documentation
What am I planning to do to next?
|  | What tasks are blocked waiting on another team member? | None