## Scrum Report
|  |  |  | Week #1 (15 hrs / week) | [6 empty] | Week #2 (15 hrs / week) | [6 empty] | Week #3 (15 hrs / week) | [6 empty] | Week #4 (15 hrs / week) | [6 empty] | Week #5 (15 hrs / week) | [6 empty] | Week #6 (15 hrs / week) | [6 empty] | Week #7 (15 hrs / week)
Sprint Number | Tasks | Task Owners | Initial Estimate (Total Sprint Hours = 60 x 7) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | D31 | D32 | D33 | D34 | D35 | D36 | D37 | D38 | D39 | D40 | D41 | D42 | D43 | D44 | D45 | D46 | D47 | D48 | D49
|  |  |  | 2022-03-20 | 2022-03-21 | 2022-03-22 | 2022-03-23 | 2022-03-24 | 2022-03-25 | 2022-03-26 | 2022-03-27 | 2022-03-28 | 2022-03-29 | 2022-03-30 | 2022-03-31 | 2022-04-01 | 2022-04-02 | 2022-04-03 | 2022-04-04 | 2022-04-05 | 2022-04-06 | 2022-04-07 | 2022-04-08 | 2022-04-09 | 2022-04-10 | 2022-04-11 | 2022-04-12 | 2022-04-13 | 2022-04-14 | 2022-04-15 | 2022-04-16 | 2022-04-17 | 2022-04-18 | 2022-04-19 | 2022-04-20 | 2022-04-21 | 2022-04-22 | 2022-04-23 | 2022-04-24 | 2022-04-25 | 2022-04-26 | 2022-04-27 | 2022-04-28 | 2022-04-29 | 2022-04-30 | 2022-05-01 | 2022-05-02 | 2022-05-03 | 2022-05-04 | 2022-05-05 | 2022-06-05 | 2022-05-07
|  |  | 420 | 420 | 411 | 402 | 393 | 384 | 375 | 366 | 357 | 348 | 339 | 330 | 321 | 312 | 303 | 294 | 285 | 276 | 267 | 258 | 249 | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123 | 114 | 105 | 96 | 87 | 78 | 69 | 60 | 51 | 42 | 33 | 24 | 15 | 6 | -3 | -12
|  |  | 420 | 420 | 420 | 400 | 400 | 380 | 360 | 360 | 360 | 340 | 340 | 320 | 320 | 300 | 300 | 300 | 300 | 280 | 280 | 260 | 240 | 240 | 240 | 240 | 220 | 220 | 200 | 180 | 180 | 180 | 160 | 140 | 140 | 140 | 120 | 120 | 120 | 100 | 80 | 80 | 80 | 80 | 60 | 60 | 40 | 40 | 20 | 20 | 0 | 0
Sprint 1 | Discussing and finalizing Technology Stack | Prashanth | 105 | Week #1 (15 hrs / week) D1: 105; Week #1 (15 hrs / week) D2: 105; Week #1 (15 hrs / week) D3: 100; Week #1 (15 hrs / week) D4: 100; Week #1 (15 hrs / week) D5: 95; Week #1 (15 hrs / week) D6: 90; Week #1 (15 hrs / week) D7: 90
| Architecture Diagram | Abhinav | 105 | Week #1 (15 hrs / week) D1: 105; Week #1 (15 hrs / week) D2: 105; Week #1 (15 hrs / week) D3: 100; Week #1 (15 hrs / week) D4: 100; Week #1 (15 hrs / week) D5: 95; Week #1 (15 hrs / week) D6: 90; Week #1 (15 hrs / week) D7: 90
| Sprint Journal | Rakshith | 105 | Week #1 (15 hrs / week) D1: 105; Week #1 (15 hrs / week) D2: 105; Week #1 (15 hrs / week) D3: 100; Week #1 (15 hrs / week) D4: 100; Week #1 (15 hrs / week) D5: 95; Week #1 (15 hrs / week) D6: 90; Week #1 (15 hrs / week) D7: 90
| Scrum Report | Iswarya | 105 | Week #1 (15 hrs / week) D1: 105; Week #1 (15 hrs / week) D2: 105; Week #1 (15 hrs / week) D3: 100; Week #1 (15 hrs / week) D4: 100; Week #1 (15 hrs / week) D5: 95; Week #1 (15 hrs / week) D6: 90; Week #1 (15 hrs / week) D7: 90
Sprint Planning
Functionalities Planning
UI Wireframe
Sprint 2 | Revising UI Wireframes, System Architecture | Abhinav |  | Week #2 (15 hrs / week) D8: 90; Week #2 (15 hrs / week) D9: 85; Week #2 (15 hrs / week) D10: 85; Week #2 (15 hrs / week) D11: 80; Week #2 (15 hrs / week) D12: 80; Week #2 (15 hrs / week) D13: 75; Week #2 (15 hrs / week) D14: 75
| Start user interface for Landing, Signup, Login Pages, Profile page | Rakshith |  | Week #2 (15 hrs / week) D8: 90; Week #2 (15 hrs / week) D9: 85; Week #2 (15 hrs / week) D10: 85; Week #2 (15 hrs / week) D11: 80; Week #2 (15 hrs / week) D12: 80; Week #2 (15 hrs / week) D13: 75; Week #2 (15 hrs / week) D14: 75
| Start Backend Setup | Iswarya |  | Week #2 (15 hrs / week) D8: 90; Week #2 (15 hrs / week) D9: 85; Week #2 (15 hrs / week) D10: 85; Week #2 (15 hrs / week) D11: 80; Week #2 (15 hrs / week) D12: 80; Week #2 (15 hrs / week) D13: 75; Week #2 (15 hrs / week) D14: 75
| Start Backend Functionalities of Login and Signup | Prashanth |  | Week #2 (15 hrs / week) D8: 90; Week #2 (15 hrs / week) D9: 85; Week #2 (15 hrs / week) D10: 85; Week #2 (15 hrs / week) D11: 80; Week #2 (15 hrs / week) D12: 80; Week #2 (15 hrs / week) D13: 75; Week #2 (15 hrs / week) D14: 75
Update Sprint Journal, Sprint Report
Sprint 3 | Complete user interface for Landing, Signup, Login and Profile Pages | Abhinav |  | Week #3 (15 hrs / week) D15: 75; Week #3 (15 hrs / week) D16: 75; Week #3 (15 hrs / week) D17: 70; Week #3 (15 hrs / week) D18: 70; Week #3 (15 hrs / week) D19: 65; Week #3 (15 hrs / week) D20: 60; Week #3 (15 hrs / week) D21: 60
| Start building user interface for Dashboard, Booking | Rakshith |  | Week #3 (15 hrs / week) D15: 75; Week #3 (15 hrs / week) D16: 75; Week #3 (15 hrs / week) D17: 70; Week #3 (15 hrs / week) D18: 70; Week #3 (15 hrs / week) D19: 65; Week #3 (15 hrs / week) D20: 60; Week #3 (15 hrs / week) D21: 60
| Start Login and Signup APIs for Hotel employees | Prashanth |  | Week #3 (15 hrs / week) D15: 75; Week #3 (15 hrs / week) D16: 75; Week #3 (15 hrs / week) D17: 70; Week #3 (15 hrs / week) D18: 70; Week #3 (15 hrs / week) D19: 65; Week #3 (15 hrs / week) D20: 60; Week #3 (15 hrs / week) D21: 60
| The rest of APIs for employee page and some APIs on customer end | Iswarya |  | Week #3 (15 hrs / week) D15: 75; Week #3 (15 hrs / week) D16: 75; Week #3 (15 hrs / week) D17: 70; Week #3 (15 hrs / week) D18: 70; Week #3 (15 hrs / week) D19: 65; Week #3 (15 hrs / week) D20: 60; Week #3 (15 hrs / week) D21: 60
Complete Backend Setup
Start Backend functionalities of Signup
Update Sprint Journal, Sprint Report, Burndown Chart, Create Stories
Sprint 4 | Admin adding hotel, Booking hotel | Rakshith |  | Week #4 (15 hrs / week) D22: 60; Week #4 (15 hrs / week) D23: 60; Week #4 (15 hrs / week) D24: 55; Week #4 (15 hrs / week) D25: 55; Week #4 (15 hrs / week) D26: 50; Week #4 (15 hrs / week) D27: 45; Week #4 (15 hrs / week) D28: 45
| User rewards, hotel search, cancel bookings | Iswarya |  | Week #4 (15 hrs / week) D22: 60; Week #4 (15 hrs / week) D23: 60; Week #4 (15 hrs / week) D24: 55; Week #4 (15 hrs / week) D25: 55; Week #4 (15 hrs / week) D26: 50; Week #4 (15 hrs / week) D27: 45; Week #4 (15 hrs / week) D28: 45
| Rooms listing, filtering rooms, guest count, user loyalty | Abhinav |  | Week #4 (15 hrs / week) D22: 60; Week #4 (15 hrs / week) D23: 60; Week #4 (15 hrs / week) D24: 55; Week #4 (15 hrs / week) D25: 55; Week #4 (15 hrs / week) D26: 50; Week #4 (15 hrs / week) D27: 45; Week #4 (15 hrs / week) D28: 45
| Integrate login, signup, profile pages with backend | Prashanth |  | Week #4 (15 hrs / week) D22: 60; Week #4 (15 hrs / week) D23: 60; Week #4 (15 hrs / week) D24: 55; Week #4 (15 hrs / week) D25: 55; Week #4 (15 hrs / week) D26: 50; Week #4 (15 hrs / week) D27: 45; Week #4 (15 hrs / week) D28: 45
Peer review of the work done so far
Functional testing backend and frontend
Create search and book room API
Update Sprint Journal, Sprint Report, Burndown Chart, Create Stories
Sprint 5 | Editing hotel details, searching for hotels | Abhinav |  | Week #5 (15 hrs / week) D29: 45; Week #5 (15 hrs / week) D30: 40; Week #5 (15 hrs / week) D31: 35; Week #5 (15 hrs / week) D32: 35; Week #5 (15 hrs / week) D33: 35; Week #5 (15 hrs / week) D34: 30; Week #5 (15 hrs / week) D35: 30
| Customer loyalty functionality, listing user bookings | Rakshith |  | Week #5 (15 hrs / week) D29: 45; Week #5 (15 hrs / week) D30: 40; Week #5 (15 hrs / week) D31: 35; Week #5 (15 hrs / week) D32: 35; Week #5 (15 hrs / week) D33: 35; Week #5 (15 hrs / week) D34: 30; Week #5 (15 hrs / week) D35: 30
| Amenities listing, dynamic price calculation on holidays, weekends | Iswarya |  | Week #5 (15 hrs / week) D29: 45; Week #5 (15 hrs / week) D30: 40; Week #5 (15 hrs / week) D31: 35; Week #5 (15 hrs / week) D32: 35; Week #5 (15 hrs / week) D33: 35; Week #5 (15 hrs / week) D34: 30; Week #5 (15 hrs / week) D35: 30
| Modify bookings, cancel bookings | Prashanth |  | Week #5 (15 hrs / week) D29: 45; Week #5 (15 hrs / week) D30: 40; Week #5 (15 hrs / week) D31: 35; Week #5 (15 hrs / week) D32: 35; Week #5 (15 hrs / week) D33: 35; Week #5 (15 hrs / week) D34: 30; Week #5 (15 hrs / week) D35: 30
Create customer and employee dashboard
Update Sprint Journal, Sprint Report, Burndown Chart, Create Stories
Create Employee login and integrate it with backend
Sprint 6 | Integrating user with user related APIs in the backend | Prashanth |  | Week #6 (15 hrs / week) D36: 30; Week #6 (15 hrs / week) D37: 25; Week #6 (15 hrs / week) D38: 20; Week #6 (15 hrs / week) D39: 20; Week #6 (15 hrs / week) D40: 20; Week #6 (15 hrs / week) D41: 20; Week #6 (15 hrs / week) D42: 15
| Intergrating admin with login and adding hotels | Rakshith |  | Week #6 (15 hrs / week) D36: 30; Week #6 (15 hrs / week) D37: 25; Week #6 (15 hrs / week) D38: 20; Week #6 (15 hrs / week) D39: 20; Week #6 (15 hrs / week) D40: 20; Week #6 (15 hrs / week) D41: 20; Week #6 (15 hrs / week) D42: 15
| Adding rooms | Abhinav |  | Week #6 (15 hrs / week) D36: 30; Week #6 (15 hrs / week) D37: 25; Week #6 (15 hrs / week) D38: 20; Week #6 (15 hrs / week) D39: 20; Week #6 (15 hrs / week) D40: 20; Week #6 (15 hrs / week) D41: 20; Week #6 (15 hrs / week) D42: 15
| Hotels listing | Iswarya |  | Week #6 (15 hrs / week) D36: 30; Week #6 (15 hrs / week) D37: 25; Week #6 (15 hrs / week) D38: 20; Week #6 (15 hrs / week) D39: 20; Week #6 (15 hrs / week) D40: 20; Week #6 (15 hrs / week) D41: 20; Week #6 (15 hrs / week) D42: 15
Update Sprint Journal, Sprint Report, Burndown Chart, Create Stories
Update Scrum Report
Sprint 7 | View Hotel bookings | Abhinav |  | Week #7 (15 hrs / week) D43: 15; Week #7 (15 hrs / week) D44: 10; Week #7 (15 hrs / week) D45: 10; Week #7 (15 hrs / week) D46: 5; Week #7 (15 hrs / week) D47: 5; Week #7 (15 hrs / week) D48: 0; Week #7 (15 hrs / week) D49: 0
| Deployment on Cloud | Prashanth |  | Week #7 (15 hrs / week) D43: 15; Week #7 (15 hrs / week) D44: 10; Week #7 (15 hrs / week) D45: 10; Week #7 (15 hrs / week) D46: 5; Week #7 (15 hrs / week) D47: 5; Week #7 (15 hrs / week) D48: 0; Week #7 (15 hrs / week) D49: 0
| Load Balacing on Cloud | Rakshith |  | Week #7 (15 hrs / week) D43: 15; Week #7 (15 hrs / week) D44: 10; Week #7 (15 hrs / week) D45: 10; Week #7 (15 hrs / week) D46: 5; Week #7 (15 hrs / week) D47: 5; Week #7 (15 hrs / week) D48: 0; Week #7 (15 hrs / week) D49: 0
| Testing on Cloud | Iswarya |  | Week #7 (15 hrs / week) D43: 15; Week #7 (15 hrs / week) D44: 10; Week #7 (15 hrs / week) D45: 10; Week #7 (15 hrs / week) D46: 5; Week #7 (15 hrs / week) D47: 5; Week #7 (15 hrs / week) D48: 0; Week #7 (15 hrs / week) D49: 0
Fix Remaining Bugs
Peer Review
Prashanth Subbiah: 15 hours / Week
Bollu Rakshith Reddy: 15 hours / Week
Iswarya Mary Gade: 15 hours / Week
Abhinav Kashyap Mandula: 15 hours / Week
420

## Burndown Chart
Sprint 1
Calender Day | Planned | Actual
2022-03-20 | 60 | 60
2022-03-21 | 48 | 60
2022-03-22 | 40 | 40
2022-03-23 | 32 | 40
2022-03-24 | 24 | 20
2022-03-25 | 18 | 20
2022-03-26 | 8 | 0
Sprint 2
Calender Day | Planned | Actual
2022-03-27 | 60 | 60
2022-03-28 | 48 | 40
2022-03-29 | 40 | 40
2022-03-30 | 32 | 20
2022-03-31 | 24 | 20
2022-04-01 | 18 | 0
2022-04-02 | 8 | 0
Sprint 3
Calender Day | Planned | Actual
2022-04-03 | 60 | 60
2022-04-04 | 48 | 60
2022-04-05 | 40 | 40
2022-04-06 | 32 | 40
2022-04-07 | 24 | 20
2022-04-08 | 18 | 20
2022-04-09 | 8 | 0
Sprint 4
Calender Day | Planned | Actual
2022-04-10 | 60 | 60
2022-04-11 | 48 | 40
2022-04-12 | 40 | 40
2022-04-13 | 32 | 40
2022-04-14 | 24 | 20
2022-04-15 | 18 | 20
2022-04-16 | 8 | 0
Sprint 5
Calender Day | Planned | Actual
2022-04-17 | 60 | 60
2022-04-18 | 48 | 40
2022-04-19 | 40 | 40
2022-04-20 | 32 | 40
2022-04-21 | 24 | 40
2022-04-22 | 18 | 20
2022-04-23 | 8 | 20
Sprint 6
Calender Day | Planned | Actual
2022-04-24 | 60 | 60
2022-04-25 | 48 | 40
2022-04-26 | 40 | 40
2022-04-27 | 32 | 20
2022-04-28 | 24 | 20
2022-04-29 | 18 | 20
2022-04-30 | 8 | 0
Sprint 7
Calender Day | Planned | Actual
2022-05-01 | 60 | 60
2022-05-02 | 48 | 40
2022-05-03 | 40 | 40
2022-05-04 | 32 | 40
2022-05-05 | 24 | 20
2022-05-06 | 18 | 20
2022-05-07 | 8 | 0